## Materials List
Materials List Input Status
No | Description | Total Sheet | Input Status |  |  |  | Review Status |  |  |  | Total Input Finish | Total Review Finish | 2024-10-13 |  |  |  | 2024-10-14 |  |  |  | 2024-10-15 |  |  |  | 2024-10-16 |  |  |  | 2024-10-17 |  |  |  | 2024-10-18 |  |  |  | 2024-10-19 |  |  |  | 2024-10-20 |  |  |  | 2024-10-21 |  |  |  | 2024-10-22 |  |  |  | 2024-10-23 |  |  |  | 2024-10-24 |  |  |  | 2024-10-25 |  |  |  | 2024-10-26 |  |  |  | 2024-10-27 |  |  |  | 2024-10-28 |  |  |  | 2024-10-29 |  |  |  | 2024-10-30 |  |  |  | Remark
|  |  | Finish Typing |  | Balance |  | Finish Review |  | Balance |  |  |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review
|  |  | QTY | % | QTY | % | QTY | % | QTY | % |  |  | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name
1 | Isometric Drawing Folder A | 227 | 227 | 100% | 0 | 0% | 227 | 100% | 0 | 0% | 227 | 227 | 4 | Feri |  |  | 26 | Feri |  |  | 35 | Feri |  |  | 45 | Feri |  |  | 43 | Feri |  |  | 50 | Feri |  |  | 24 | Yuli Feri |  |  |  |  | 227 | Lutfi Cecep
| Isometric Drawing Folder B | 307 | 307 | 100% | 0 | 0% | 307 | 100% | 0 | 0% | 307 | 307 | 7 | Cecep |  |  | 33 | Cecep |  |  | 37 | Cecep |  |  | 64 | Cecep |  |  | 40 | Cecep |  |  | 41 | Cecep |  |  | 85 | Cecep Lutfi | 35 | Lutfi |  |  | 100 | Yuli Feri |  |  | 172 | Feri Yuli
| Isometric Drawing Folder C1 | 130 | 130 | 100% | 0 | 0% | 130 | 100% | 0 | 0% | 130 | 130 | 28 | Lutfi |  |  | 102 | Lutfi | [8 empty] | 10 | Lutfi |  |  | 110 | Lutfi |  |  | 10 | Lutfi
| Isometric Drawing Folder C2 | 99 | 99 | 100% | 0 | 0% | 99 | 100% | 0 | 0% | 99 | 99 |  |  |  |  | 9 | Lutfi |  |  | 85 | Lutfi |  |  | 5 | Lutfi |  |  |  |  | 50 | Lutfi |  |  | 49 | Lutfi
| Isometric Drawing Folder D | 313 | 313 | 100% | 0 | 0% | 313 | 100% | 0 | 0% | 313 | 313 | 9 | Yuli |  |  | 30 | Yuli |  |  | 65 | Yuli |  |  | 49 | Yuli |  |  | 50 | Yuli |  |  | 110 | Yuli | [8 empty] | 313 | OCP
| Isometric Drawing Folder E | 163 | 163 | 100% | 0 | 0% | 163 | 100% | 0 | 0% | 163 | 163 |  |  |  |  | 50 | OCP |  |  | 70 | OCP |  |  | 43 | OCP | 163 | OCP
| Isometric Drawing Folder F1 | 150 | 150 | 100% | 0 | 0% | 150 | 100% | 0 | 0% | 150 | 150 | [12 empty] | 12 | OCP |  |  | 40 | OCP |  |  | 50 | OCP |  |  | 48 | OCP | 150 | OCP
| Isometric Drawing Folder F2 | 128 | 128 | 100% | 0 | 0% | 128 | 100% | 0 | 0% | 128 | 128 | [12 empty] | 81 | Lutfi |  |  | 15 | Lutfi |  |  | 32 | Lutfi | 128 | Lutfi
| Isometric Drawing Folder G | 79 | 0 | 0% | 79 | 100% | 0 | 0% | 79 | 100% | 0 | 0 | [72 empty] | No BOM in Drawing, manual taking off
| Total | 1596 | 1517 | 95.05% | 79 | 4.95% | 1517 | 95.05% | 79 | 4.95% | 1517 | 1517 | 48 |  | 0 |  | 250 |  | 0 |  | 292 |  | 0 |  | 299 |  | 173 |  | 188 |  | 160 |  | 283 |  | 187 |  | 157 |  | 185 |  | 0 |  | 640 |  | 0 |  | 172 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Re-draw CAD drawing
No | Description | Total Sheet | Input Status |  |  |  | Review Status |  |  |  | Total Input Finish | Total Review Finish | 2024-10-13 |  |  |  | 2024-10-14 |  |  |  | 2024-10-15 |  |  |  | 2024-10-16 |  |  |  | 2024-10-17 |  |  |  | 2024-10-17 |  |  |  | 2024-10-19 |  |  |  | 2024-10-20 |  |  |  | 2024-10-21 |  |  |  | 2024-10-22 |  |  |  | 2024-10-23 |  |  |  | 2024-10-24 |  |  |  | 2024-10-25 |  |  |  | 2024-10-26 |  |  |  | 2024-10-27 |  |  |  | 2024-10-28 |  |  |  | 2024-10-29 |  |  |  | 2024-10-30 |  |  |  | Remark
|  |  | Finish re-draw |  | Balance |  | Finish Review |  | Balance |  |  |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review |  | Redraw |  | Review
|  |  | QTY | % | QTY | % | QTY | % | QTY | % |  |  | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name
1 | P&I Diagram (MA 42) | 50 | 50 | 100% | 0 | 0% | 0 | 0% | 50 | 100% | 50 | 0 | 3 | Ilham |  |  | 6 | Ilham |  |  | 4 | Ilham |  |  | 5 | Ilham |  |  | 7 | Ilham |  |  | 5 | Ilham |  |  | 6 | Ilham |  |  | 4 | Ilham |  |  | 4 | Ilham |  |  | 6 | Ilham
2 | Isometric Drawing Folder A | 227 | 219 | 96.48% | 8 | 3.524% | 0 | 0% | 227 | 100% | 219 | 0 | 2 | Ikmal |  |  | 5 | Ikmal & Reza |  |  | 32 | Reza Ikmal |  |  | 34 | Reza Ikmal |  |  | 35 | Reza Ikmal |  |  | 32 | Reza Ikmal |  |  | 30 | Reza Ikmal |  |  | 9 | Reza |  |  | 20 | Reza Ikmal |  |  | 20 | Reza Ikmal
| Isometric Drawing Folder B | 307 | 0 | 0% | 307 | 100% | 0 | 0% | 307 | 100% | 0 | 0
| Isometric Drawing Folder C1 | 130 | 0 | 0% | 130 | 100% | 0 | 0% | 130 | 100% | 0 | 0
| Isometric Drawing Folder C2 | 99 | 0 | 0% | 99 | 100% | 0 | 0% | 99 | 100% | 0 | 0
| Isometric Drawing Folder D | 216 | 8 | 3.704% | 208 | 96.3% | 0 | 0% | 216 | 100% | 8 | 0 | [36 empty] | 8 | Aat | [34 empty] | Actual sheets : 216 pg
| Isometric Drawing Folder E | 163 | 3 | 1.84% | 160 | 98.16% | 0 | 0% | 163 | 100% | 3 | 0 | [32 empty] | 3 | PT. Tata
| Isometric Drawing Folder F1 | 150 | 0 | 0% | 150 | 100% | 0 | 0% | 150 | 100% | 0 | 0
| Isometric Drawing Folder F2 | 128 | 0 | 0% | 128 | 100% | 0 | 0% | 128 | 100% | 0 | 0
| Isometric Drawing Folder G | 79 | 54 | 68.35% | 25 | 31.65% | 0 | 0% | 79 | 100% | 54 | 0 | [24 empty] | 7 | Anif Latif |  |  | 9 | Anif |  |  | 20 | Anif Latif |  |  | 18 | Anif Latif
3 | Structural Drawing | 291 | 1 | 0.3436% | 290 | 99.66% | 0 | 0% | 291 | 100% | 1 | 0 | [32 empty] | 1 | PT. Tata | [38 empty] | Tonight start draft
| Total | 1840 | 335 | 18.21% | 1505 | 81.79% | 0 | 0% | 1840 | 100% | 335 | 0 | 5 |  | 0 |  | 11 |  | 0 |  | 36 |  | 0 |  | 39 |  | 0 |  | 42 |  | 0 |  | 37 |  | 0 |  | 43 |  | 0 |  | 22 |  | 0 |  | 48 |  | 0 |  | 52 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Note:
1. Input material list into ISO drawing : Lutfi (40sheets). Cecep (40sheets) & Yuli (30sheets)

## 2A PUNCHLIST
Punch List Work Area 2A
No. | Work Description | Achivon Scope | HJU Scope | Work Qty | Unit | Work Complete | % | Work Remain | % | Total | 2024-10-10 | 2024-10-11 | 2024-10-12 | Remark
1 | Touch up Paint | Touch up Work | Provide Painting | 1 | point | 1 | 100% | 0 | 0% | 1 |  | 1
2 | Flange & Gasket Installation (tightening) | Install Gasket & Tightening | Flow Check Flange Painting | 3 | ea | 3 | 100% | 0 | 0% | 3 | 3 |  |  | Torque 6 ea Flange Joint
3 | Support Fabrication & Installation | Fabrication & Install | Provide Material & Painting after Install | 8 | ea | 3 | 37.5% | 5 | 62.5% | 3 | 3 |  |  | Material not yet receive
4 | Pickling Welding Joint | Material & Pickling work | - | 648 | Joint | 648 | 100% | 0 | 0% | 648 | 240 | 408
|  |  | TOTAL | 660 | ITEM | 655 | 99.24% | 5 | 0.7634% | 655 | 246 | 409

## DRAWING INPUT STATUS
Drawing List Input Status
No | Description | Total Sheet | Input Status |  |  |  | Review Status |  |  |  | Total Input Finish | Total Review Finish | Previous Input | 2024-10-11 |  |  |  | 2024-10-12 |  |  |  | 2024-10-13 |  |  |  | Remark
|  |  | Finish Typing |  | Balance |  | Finish Review |  | Balance |  |  |  |  | Input |  | Review |  | Input |  | Review |  | Input |  | Review
|  |  | QTY | % | QTY | % | QTY | % | QTY | % |  |  |  | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name | QTY | Name
1 | P&I Diagram (MA 42) | 50 | 50 | 100% | 0 | 0% | 50 | 100% | 0 | 0% | 50 | 50 | 50 |  | Ilham |  |  |  |  | 50 | Ilham
2 | Isometric Drawing Folder A | 227 | 227 | 100% | 0 | 0% | 227 | 100% | 0 | 0% | 227 | 227 |  | 200 | Ilham |  |  | 27 | Reza | 227 | Ilham
| Isometric Drawing Folder B | 307 | 307 | 100% | 0 | 0% | 307 | 100% | 0 | 0% | 307 | 307 | 307 |  | Cecep |  |  |  |  | 307 | OCP
| Isometric Drawing Folder C1 | 130 | 130 | 100% | 0 | 0% | 130 | 100% | 0 | 0% | 130 | 130 | 130 |  | Feri |  |  |  |  | 130 | OCP
| Isometric Drawing Folder C2 | 99 | 99 | 100% | 0 | 0% | 99 | 100% | 0 | 0% | 99 | 99 | 99 |  | Feri |  |  |  |  | 99 | OCP
| Isometric Drawing Folder D | 313 | 313 | 100% | 0 | 0% | 313 | 100% | 0 | 0% | 313 | 313 | 313 |  | Yuli |  |  |  |  | 313 | OCP
| Isometric Drawing Folder E | 163 | 163 | 100% | 0 | 0% | 163 | 100% | 0 | 0% | 163 | 163 | 163 |  | Yuli |  |  |  |  | 163 | Lutfi
| Isometric Drawing Folder F1 | 150 | 150 | 100% | 0 | 0% | 150 | 100% | 0 | 0% | 150 | 150 |  | 150 | Feri |  |  |  |  | 150 | OCP
| Isometric Drawing Folder F2 | 128 | 128 | 100% | 0 | 0% | 128 | 100% | 0 | 0% | 128 | 128 |  | 128 | Ikmal |  |  |  |  | 128 | Ilham
| Isometric Drawing Folder G | 79 | 79 | 100% | 0 | 0% | 79 | 100% | 0 | 0% | 79 | 79 |  | 79 | Reza |  |  |  |  | 79 | Ilham
3 | Structural Drawing | 291 | 291 | 100% | 0 | 0% | 0 | 0% | 291 | 100% | 291 | 0 | [5 empty] | 291 | Cecep / Reza
4 | Electrical Folder A | 157 | 157 | 100% | 0 | 0% | 157 | 100% | 0 | 0% | 157 | 157 | [5 empty] | 157 | Lutfi | 157 | Ilham
5 | Electrical Folder B | 93 | 93 | 100% | 0 | 0% | 93 | 100% | 0 | 0% | 93 | 93 | [5 empty] | 93 | Lutfi | 93 | Ilham
7 | Electrical Owner | 41 | 41 | 100% | 0 | 0% | 41 | 100% | 0 | 0% | 41 | 41 | [5 empty] | 41 | Ilham | 41 | Lutfi
8 | Chemetic Instrument 1 of 3 | 205 | 205 | 100% | 0 | 0% | 205 | 100% | 0 | 0% | 205 | 205 | [5 empty] | 205 | Ikmal & Reza | 205 | Ilham
9 | Chemetic Instrument 2 of 3 | 213 | 213 | 100% | 0 | 0% | 0 | 0% | 213 | 100% | 213 | 0 | [5 empty] | 213 | Feri
10 | Chemetic Instrument 3 of 3 | 152 | 152 | 100% | 0 | 0% | 152 | 100% | 0 | 0% | 152 | 152 | [5 empty] | 152 | Yuli | 152 | Ilham
| Total | 2798 | 2798 | 100% | 0 | 0% | 2294 | 81.99% | 504 | 18.01% | 2798 | 2294 | 1062 | 557 |  | 0 |  | 1179 |  | 2294 |  | 0 |  | 0

## Materials List Vendor
Re-draw CAD drawing
No | Description | Total Sheet | Vendor | Plan QTY | CAD DRAWING STATUS |  |  |  | TOTAL ACTUAL COMPLETED | PREVIOUS PROGRESS (UP TO 22 Oct 2024) | PLANNING
[5 empty] | Finish Re-draw |  | Balance |  |  |  | 2024-10-23 |  | 2024-10-24 |  | 2024-10-25 |  | 2024-10-26 |  | 2024-10-27 |  | 2024-10-28 |  | 2024-10-29 |  | 2024-10-30
[5 empty] | QTY | % | QTY | % |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
1 | P&I Diagram (MA 42) | 50 | ACHIVON | 50 | 50 | 100% | 0 | 0% | 50 | 50
2 | Isometric Drawing Folder A | 227 | ACHIVON | 227 | 227 | 100% | 0 | 0% | 227 | 219 | 8 | 8 | [15 empty] | 120 | 67 | 53
| Isometric Drawing Folder B | 307 | ACHIVON | 267 | 130 | 42.35% | 177 | 57.65% | 130 | 0 | 27 | 33 | 40 | 25 | 40 | 10 | 40 | 10 | 40 | 10 | 40 | 21 | 40 | 21 | 40
| Isometric Drawing Folder C1 | 130 | NUR | 130 | 51 | 39.23% | 79 | 60.77% | 51 | 0 |  |  | 55 | 5 | 55 | 6 | 20 | 4 |  |  |  | 10 |  | 26
| Isometric Drawing Folder C2 | 99 | NUR | 99 | 76 | 76.77% | 23 | 23.23% | 76 | 0 |  |  |  | 15 |  | 16 | 35 | 12 | 55 | 17 | 9 | 13 |  | 3
| Isometric Drawing Folder D | 216 | AGUS | 216 | 77 | 35.65% | 139 | 64.35% | 77 | 8 | 15 | 4 | 40 | 17 | 40 | 6 | 40 | 4 | 40 |  | 33 | 21 |  | 17
| Isometric Drawing Folder E | 163 | AGUS | 163 | 84 | 51.53% | 79 | 48.47% | 84 | 3 |  | 5 | 30 | 4 | 30 | 24 | 30 | 18 | 30 |  | 37 | 4 | 3 | 26
| Isometric Drawing Folder F1 | 150 | NUR | 101 | 115 | 76.67% | 35 | 23.33% | 115 | 0 |  |  |  | 25 |  | 26 |  | 20 |  | 12 | 46 | 17 | 55 | 15 | 49
| Isometric Drawing Folder F2 | 128 | AGUS | 67 | 23 | 17.97% | 105 | 82.03% | 23 | 0 |  |  |  | 11 |  | 7 |  | 5 |  |  |  |  | 67 |  | 61
| Isometric Drawing Folder G | 79 | AGUS | 79 | 79 | 100% | 0 | 0% | 79 | 54 | 25 | 25
3 | Structural Drawing F1 | 150 | TEGUH | 271 | 94 | 62.67% | 56 | 37.33% | 94 | 1 |  |  | 45 | 15 | 45 | 18 | 45 | 17 | 45 | 5 | 45 | 20 | 45 | 18 | 20 |  |  | 64 |  | 17
| Structural Drawing F2 | 141 | UNI STUDENTS | 0 | 91 | 64.54% | 50 | 35.46% | 91 | [6 empty] | 17 |  | 19 |  | 10 |  | 22 |  | 23
| Total | 1840 |  | 1670 | 1097 | 59.62% | 743 | 40.38% | 1097 | 335 | 75 | 75 | 210 | 117 | 210 | 130 | 210 | 109 | 210 | 54 | 210 | 128 | 210 | 149 | 170 | 0
|  |  | BACKLOG | 573
| AGUS (8 org) | 586 | D + E + F2 + G |  | 263 | 44.88% | 323 | 55.12% | 263 | 65 | 40 | 34 | 70 | 32 | 70 | 37 | 70 | 27 | 70 | 0 | 70 | 25 | 70 | 43 | 61 | 0 | 521
| TEGUH (5 org) | 150 | STRUCTURAL-1 |  | 94 | 62.67% | 56 | 37.33% | 94 | 1 | 0 | 0 | 45 | 15 | 45 | 18 | 45 | 17 | 45 | 5 | 45 | 20 | 45 | 18 | 20 | 0 | 290
| NUR (5 org) | 379 | C1 + C2 + F1 |  | 242 | 63.85% | 137 | 36.15% | 242 | 0 | 0 | 0 | 55 | 45 | 55 | 48 | 55 | 36 | 55 | 29 | 55 | 40 | 55 | 44 | 49 | 0 | 379
| ACHIVON | 584 | P&ID + A + B |  | 407 | 69.69% | 177 | 30.31% | 407 | 269 | 35 | 41 | 40 | 25 | 40 | 10 | 40 | 10 | 40 | 10 | 40 | 21 | 40 | 21 | 40 | 0 | 315
| UNI STUDENTS (10 org) | 141 | STRUCTURAL-2 |  | 91 | 64.54% | 50 | 35.46% | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 19 | 0 | 10 | 0 | 22 | 0 | 23 | 0 | 0
| Total | 1840 |  |  | 1097 | 59.62% | 743 | 40.38% | 1097 | 335 | 75 | 75 | 210 | 117 | 210 | 130 | 210 | 109 | 210 | 54 | 210 | 128 | 210 | 149 | 170 | 0 | 1505
[15 empty] | Target Balance | 1010
[15 empty] | Actual Balance | 743
[15 empty] | Backlog | -267
| AGUS (8 org) | Rp. 30,000/sheet
| TEGUH (5 org) | Rp. 45,000/sheet
| NUR (5 org) | Rp. 35,000/sheet

## Materials List Vendor (ACTUAL)
Re-draw CAD drawing
No | Description | Total Sheet | Vendor | Plan QTY | CAD DRAWING STATUS |  |  |  | TOTAL ACTUAL COMPLETED | PREVIOUS PROGRESS (UP TO 22 Oct 2024) | PLANNING
[5 empty] | Finish Re-draw |  | Balance |  |  |  | 2024-10-23 |  | 2024-10-24 |  | 2024-10-25 |  | 2024-10-26 |  | 2024-10-27 |  | 2024-10-28 |  | 2024-10-29 |  | 2024-10-30
[5 empty] | QTY | % | QTY | % |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
1 | P&I Diagram (MA 42) | 50 | ACHIVON | 50 | 50 | 100% | 0 | 0% | 50 | 50
2 | Isometric Drawing Folder A | 227 | ACHIVON | 227 | 227 | 100% | 0 | 0% | 227 | 219 | 8 | 8 | [15 empty] | 120 | 45 | 75
| Isometric Drawing Folder B | 307 | ACHIVON | 227 | 109 | 35.5% | 198 | 64.5% | 109 | 0 | 27 | 33 | 40 | 25 | 40 | 10 | 40 | 10 | 40 | 10 | 40 | 21 | 40 |  | 40
| Isometric Drawing Folder C1 | 130 | NUR | 130 | 25 | 19.23% | 105 | 80.77% | 25 | 0 |  |  | 55 | 5 | 55 | 6 | 20 | 4 |  |  |  | 10
| Isometric Drawing Folder C2 | 99 | NUR | 99 | 61 | 61.62% | 38 | 38.38% | 61 | 0 |  |  |  | 15 |  | 16 | 35 |  | 55 | 17 | 9 | 13
| Isometric Drawing Folder D | 216 | AGUS | 216 | 69 | 31.94% | 147 | 68.06% | 69 | 8 | 15 | 4 | 40 | 17 | 40 | 6 | 40 | 13 | 40 |  | 33 | 21
| Isometric Drawing Folder E | 163 | AGUS | 160 | 50 | 30.67% | 113 | 69.33% | 50 | 3 |  | 5 | 30 | 4 | 30 | 24 | 30 | 10 | 30 |  | 37 | 4 | 3
| Isometric Drawing Folder F1 | 150 | NUR | 46 | 91 | 60.67% | 59 | 39.33% | 91 | 0 |  |  |  | 25 |  | 26 |  | 11 |  | 12 | 46 | 17 | 55 |  | 49
| Isometric Drawing Folder F2 | 128 | AGUS | 0 | 18 | 14.06% | 110 | 85.94% | 18 | 0 |  |  |  | 11 |  | 7 | [6 empty] | 67 |  | 61
| Isometric Drawing Folder G | 79 | AGUS | 79 | 79 | 100% | 0 | 0% | 79 | 54 | 25 | 25
3 | Structural Drawing F1 | 150 | TEGUH | 226 | 76 | 50.67% | 74 | 49.33% | 76 | 1 |  |  | 45 | 15 | 45 | 18 | 45 | 17 | 45 | 5 | 45 | 20 | 45 |  | 20 |  |  | 64 |  | 17
| Structural Drawing F2 | 141 | UNI STUDENTS | 0 | 68 | 48.23% | 73 | 51.77% | 68 | [6 empty] | 17 |  | 19 |  | 10 |  | 22
| Total | 1840 |  | 1460 | 923 | 50.16% | 917 | 49.84% | 923 | 335 | 75 | 75 | 210 | 117 | 210 | 130 | 210 | 84 | 210 | 54 | 210 | 128 | 210 | 0 | 170 | 0
|  |  | BACKLOG | 537
| AGUS (8 org) | 586 | D + E + F2 + G |  | 216 | 36.86% | 370 | 63.14% | 216 | 65 | 40 | 34 | 70 | 32 | 70 | 37 | 70 | 23 | 70 | 0 | 70 | 25 | 70 | 0 | 61 | 0 | 521
| TEGUH (5 org) | 150 | STRUCTURAL-1 |  | 76 | 50.67% | 74 | 49.33% | 76 | 1 | 0 | 0 | 45 | 15 | 45 | 18 | 45 | 17 | 45 | 5 | 45 | 20 | 45 | 0 | 20 | 0 | 290
| NUR (5 org) | 379 | C1 + C2 + F1 |  | 177 | 46.7% | 202 | 53.3% | 177 | 0 | 0 | 0 | 55 | 45 | 55 | 48 | 55 | 15 | 55 | 29 | 55 | 40 | 55 | 0 | 49 | 0 | 379
| ACHIVON | 584 | P&ID + A + B |  | 386 | 66.1% | 198 | 33.9% | 386 | 269 | 35 | 41 | 40 | 25 | 40 | 10 | 40 | 10 | 40 | 10 | 40 | 21 | 40 | 0 | 40 | 0 | 315
| UNI STUDENTS (10 org) | 141 | STRUCTURAL-2 |  | 68 | 48.23% | 73 | 51.77% | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 19 | 0 | 10 | 0 | 22 | 0 | 0 | 0 | 0
| Total | 1840 |  |  | 923 | 50.16% | 917 | 49.84% | 923 | 335 | 75 | 75 | 210 | 117 | 210 | 130 | 210 | 84 | 210 | 54 | 210 | 128 | 210 | 0 | 170 | 0 | 1505
[15 empty] | Target Balance | 1010
[15 empty] | Actual Balance | 917
[15 empty] | Backlog | -93
| AGUS (8 org) | Rp. 30,000/sheet
| TEGUH (5 org) | Rp. 45,000/sheet
| NUR (5 org) | Rp. 35,000/sheet

## Materials List Vendor (2)
Re-draw CAD drawing
No | Description | Vendor | CAD DRAWING STATUS |  |  | material table
|  |  | Total Sheet | Received | Balance | Total Sheet | Material Table Completed | Final Review | Material Table N/A
1 | P&I Diagram (MA 42) | ACHIVON | 50 | 50 | 0 | N/A
2 | Isometric Drawing Folder A | ACHIVON | 226 | 226 | 0 | 226 | 226 | 94 | 0
| Isometric Drawing Folder B | ACHIVON | 117 | 117 | 0 | 117 | 117 | 117 | 0
| Isometric Drawing Folder B | UNI STUDENTS | 189 | 1 | 188 | 1 |  |  | 1
| Isometric Drawing Folder C1 | NUR | 130 | 130 | 0 | 130 | 130 | 130 | 0
| Isometric Drawing Folder C2 | NUR | 99 | 99 | 0 | 99 | 68 | 35 | 31
| Isometric Drawing Folder D | AGUS | 215 | 213 | 2 | 213 | 160 | 160 | 53
| Isometric Drawing Folder E | AGUS | 161 | 161 | 0 | 161 | 0 |  | 161
| Isometric Drawing Folder F1 | NUR | 147 | 147 | 0 | 147 | 114 |  | 33
| Isometric Drawing Folder F2 | AGUS | 156 | 156 | 0 | 156 | 0 |  | 156
| Isometric Drawing Folder G | AGUS | 81 | 81 | 0 | N/A
3 | Structural Drawing F1 | TEGUH | 144 | 37 | 107 | N/A
| Structural Drawing F2 | UNI STUDENTS | 141 | 91 | 50 | N/A
| Total |  | 1856 | 1509 | 347 | 1250 | 815 | 536 | 435
81.3%